## Slide 1
CONCLUSIVE RISK & SECURITY LOG (MMP)
Part A: Review of Sprint 1 Risks
Student Name: Yoldoshali Esonaliyev (2461947)
Role: Project Manager (Secondary: Security Engineer)
Group Name: MIX
Ref ID | Original Risk Description | Did it occur? (Y/N) | Status (Closed / Active / Mitigated) | Action Taken / Outcome
R01 | Team timezone + coursework overlap compressing coding hours into evenings, causing sprint velocity under-estimation. | Y | Mitigated | Introduced fixed daily stand-up at 20:00 and a mid-sprint Thursday checkpoint. Paired every primary role with a secondary owner so blocked work could be picked up.
R02 | Requirements creep from stakeholders pulling scope beyond the MVP target (loyalty, subscriptions, 3D viewer all competing for time). | Y | Closed | Ran formal scope-triage (MMP / Post-MMP / Nice-to-have). Moved non-MMP items out of Sprint 2 backlog, kept visible for stakeholders.
R03 | Local environment drift — backend Docker cache retaining stale seed.js data after migrations, blocking developers. | Y | Closed | Documented `docker compose build --no-cache backend` workaround in CLAUDE.md. Added to onboarding checklist. No recurrence after 10 Feb.
R04 | Insecure session-token handling in the legacy auth middleware flagged as non-compliant for the target market. | Y | Mitigated | Rewrote auth middleware with JWT refresh-token rotation. Security-review completed by PM in shadow Security-Engineer role. Carried one hardening ticket to Sprint 3.
R05 | Port 80 conflict on local Kali Linux preventing nginx proxy from binding during development. | Y | Closed | Workaround: bypass nginx proxy and expose frontend directly on port 3000 during dev. Production compose unaffected.

## Slide 2
Part B: New Risks for Sprint 2 / MMP (Identification)
Identify new technical or delivery risks specific to the final stage (e.g., Hosting failure, Security vulnerabilities).
Ref ID | New Risk Category | Risk Description / Threat | Likelihood (1-5) | Impact (1-5) | Score | Mitigation Strategy
R06 | Payments | Payme / Click local payment gateway integration may fail certification or callback webhook verification, blocking real-money flow. | 3 | 5 | 15 | Build with sandbox credentials first; implement HMAC webhook signature verification; maintain a Stripe test-mode fallback so UI can be demoed even if Uzbek gateways reject.
R07 | Security | AI chat endpoint (Anthropic Claude) could leak internal prompts or be abused for prompt-injection from untrusted user input. | 3 | 4 | 12 | Server-side prompt templating only — user input never concatenated into system prompt. Rate-limit per-user. Log and redact PII before sending. Response-content policy filter before returning to client.
R08 | Delivery / Scope | i18n (UZ/RU/EN), PWA and real-time WebSocket table availability all competing for Sprint 3 time — risk of partial delivery. | 4 | 3 | 12 | PM to lock Sprint 3 scope to two of the three on Day 1 based on business value. WebSocket prioritised (user-visible). PWA deferred to post-launch if needed.
R09 | Infrastructure | Hosting failure or cold-start latency on production — single-region deploy with no load balancing, unable to absorb a traffic spike at launch. | 2 | 5 | 10 | Dockerised stack with `deploy.sh` ready for rapid re-deploy. Pre-launch load test with k6 against staging. Add CDN for static assets. Document rollback procedure.
R10 | Data / Database | `price_per_hour` column absence in schema — using `price_multiplier * basePrice` calculation instead. Risk of pricing mismatch when venues update rates. | 3 | 3 | 9 | Add real `price_per_hour` column in Sprint 3 migration, backfill from existing multiplier. Wrap pricing logic in a single `getEffectivePrice()` service so call-sites do not diverge.
Part C: Risk Management Insights
Briefly describe how your team handled uncertainty during the project. Did you encounter any "Unknown Unknowns" (risks you didn't plan for)?
Our team handled uncertainty through three practices. First, role redundancy — every primary role had a secondary owner, so a blocked ticket never stalled on a single person. Second, visible blockers — we added a Blocked column on the Notion Task Board so impediments surfaced in the daily stand-up instead of being buried in chat. Third, scope triage — rather than trying to absorb stakeholder requests mid-sprint, we labelled each request MMP / Post-MMP / Nice-to-have and only the MMP bucket entered the active sprint. Unknown unknowns we encountered: (1) the AI chat and 3D viewer started in parallel turned out to integrate poorly because both consumed the same backend session context — we paused 3D for 48 hours and brought it back sequentially. (2) The Kali Linux development host held port 80 via a system service that was not obvious from docker-compose, discovered only when the nginx proxy refused to bind — resolved by switching dev traffic to port 3000. (3) The backend Docker cache retained stale seed data silently after migrations; the fix (`--no-cache`) was fast once found but the initial diagnosis took an evening. All three are now documented in CLAUDE.md so they become known risks in future sprints rather than surprises.